## Phase 1 — Tennis foundation and
# | Title | Status
1 | Schema, core tables, and migration runner | Done
2 | Labeled demo data and seeding | Done
3 | Reporting view and integrity constraints | Done
4 | Tennis ETL from the Sackmann archive | Done
5 | Leakage-safe feature table (player_game_features) | Done
6 | Feature integrity, config validation, drift guards | Done
7 | Baseline model (rolling average + context) | Done
8 | Walk-forward backtesting harness | Done
9 | Quantile GBM (LightGBM, 0.1/0.5/0.9) | Done
10 | Ensemble layer (weighted average, out-of-fold weights) | Next
11 | Odds ingestion and player identity resolution | Next
12 | Full historical backtest, calibration, model card | Next
13 | Bayesian/hierarchical layer — gated, may be skipped | Projected
14 | Edge-case stress tests (retirements, surface transitions, sparse history) | Projected
15 | Phase 1 exit: tennis freeze and documentation | Projected

## Phase 2 — MLB as the team-sport
# | Title
16 | MLB data source evaluation and schema extension
17 | MLB ETL (games, lineups, box scores)
18 | MLB feature engineering (park factors, pitcher matchup, lineup slot)
19 | MLB models via the existing model code — the portability test
20 | MLB odds ingestion and backtest
21 | Phase 2 exit: MLB validation and comparison to tennis

## Phase 3 — Generalization (Weeks
# | Title
22 | Sport registry and config-driven pipeline entry points
23 | Extract sport-agnostic feature and model interfaces
24 | Cross-sport regression suite
25 | "Add a new sport" runbook plus a dry run on a throwaway sport

## Phase 4 — NFL (Weeks 31–42)
# | Title
26 | NFL data source evaluation and acquisition
27 | NFL ETL (games, snap counts, depth charts)
28 | NFL feature engineering (usage, weather, injury status)
29 | NFL models through the generic path
30 | NFL odds ingestion and backtest
31 | NFL calibration and validation
32 | Phase 4 exit: NFL accuracy sign-off

## Phase 5 — Dashboard, live opera
# | Title
33 | Dashboard data layer hardening (vw_fact_player_prop_odds only)
34 | Dashboard UI build
35 | Scheduled daily prediction runs
36 | Monitoring, drift detection, alerting
37 | Paper-trading shadow test
38 | Go-live readiness review